## Sheet1
Month | Time Frame | When | Event | Task | Person Responsible
1 | January | Early | SLC | Contact Sherry regarding changes in online testing, costs, etc.
1 | January | Early | SLC | Determine Home Event Deadlines
1 | January | Early | SLC | Determine registration deadline
1 | January | Early | SLC | Determine registration process and procedures
1 | January | Early | SLC | Determine room costs for members
1 | January | Early | SLC | Email advisors regarding room costs
1 | January | Early | SLC | Post updated info on website
1 | January | Early | SLC | Revise sponsorship letter
1 | January | Early | SLC | Revise what to include on registration--t-shirt size? Special meals? Other accommodations?
1 | January | Early | SLC | Send out sponsorship letters
1 | January | Early | SLC | Send pin design to printers
1 | January | Early | SLC | Solicit door prizes
1 | January | Mid | SLC | Email registrations/registration process to advisors
1 | January | Mid | SLC | Executive Committee Conference Call
2 | February | Early | SLC | Assess materials needed for conference (certificate paper, nametags, etc.)
2 | February | Early | SLC | Determine advisor roles and judging
2 | February | Early | SLC | Determine agenda for days
2 | February | Early | SLC | Determine who will be in Headquarters
2 | February | Early | SLC | Email advisors requesting nominations for Advisor of the Year
2 | February | Early | SLC | Executive Committee Conference Call
2 | February | Early | SLC | Follow up on sponsorships
2 | February | Early | SLC | Get advisor gifts
2 | February | Early | SLC | Get judges' gifts
2 | February | Early | SLC | Secure workshop speaker(s)
2 | February | Early | SLC | Send out letters to potential judges
2 | February | Early | SLC | Send t-shirt design to printers
2 | February | Early | SLC | Update Excel program to print certificates
2 | February | Mid | SLC | Buy conference materials (certificate paper, nametags, etc.)
2 | February | Mid | SLC | Determine number of awards needed
2 | February | Mid | SLC | Forward sponsorship information to person creating awards banquet slide show
2 | February | Mid | SLC | Get Secretary's Report for program
2 | February | Mid | SLC | Get Treasurer's Report for program
2 | February | Mid | SLC | Get workshop speakers' needs (AV, pens, flipchart, etc.)
3 | March | Early | SLC | Collect Home Events
3 | March | Early | SLC | Contact WCAX and other media to cover event
3 | March | Early | SLC | Create/Revise Banquet program
3 | March | Early | SLC | Determine Advisor of the Year
3 | March | Early | SLC | Determine number of judges needed
3 | March | Early | SLC | Determine outgoing state officer gifts/flowers
3 | March | Early | SLC | Determine which state officers will help each workshop presenter
3 | March | Early | SLC | Executive Committee Conference Call
3 | March | Early | SLC | Order Advisor of the Year plaque if not already done
3 | March | Early | SLC | Request years of service from advisors (put in registration?)
3 | March | Early | SLC | Send out letters to confirmed judges
3 | March | Early | SLC | Submit rooming list
3 | March | Mid | SLC | Executive Committee Conference Call
3 | March | Mid | SLC | Order plaques
3 | March | Week Before | SLC | Adjust script as necessary
3 | March | Week Before | SLC | Be sure all phone numbers are in cell phone and master listing in HQ
3 | March | Week Before | SLC | Confirm meal and beverage counts
3 | March | Week Before | SLC | Confirm necessary AV materials with hotel (mikes, internet, etc.)
3 | March | Week Before | SLC | Confirm with hotel tablecloth colors, pipe and draping, etc.
3 | March | Week Before | SLC | Create a flash drive of all necessary documents (hard copies, too, if desired)
3 | March | Week Before | SLC | Create evaluation form
3 | March | Week Before | SLC | Create nametags for attendees
3 | March | Week Before | SLC | Create program
3 | March | Week Before | SLC | Determine any retiring advisors
3 | March | Week Before | SLC | Determine gift/flowers for retiring advisors
3 | March | Week Before | SLC | Email reminders to advisors--dress codes, permission slips, big trophies, etc.
3 | March | Week Before | SLC | Get t-shirts
3 | March | Week Before | SLC | Make signs if needed
3 | March | Week Before | SLC | Order outgoing state officer gifts/flowers
3 | March | Week Before | SLC | Pick up plaques
3 | March | Week Before | SLC | Pick up t-shirts
3 | March | Week Before | SLC | Print Banquet program
3 | March | Week Before | SLC | Print Certificates for online testing winners
3 | March | Week Before | SLC | Print certificates for retiring advisors
3 | March | Week Before | SLC | Print Certificates of Participation
3 | March | Week Before | SLC | Print evaluation form
3 | March | Week Before | SLC | Print program
3 | March | Week Before | SLC | Print years of service certificates for advisors (5, 10, 15, 20, etc.)
3 | March | Week Before | SLC | Provide hotel with meal numbers
3 | March | Week Before | SLC | Purchase envelopes for registration packets
3 | March | Week Before | SLC | Purchase nametags for registration packets
3 | March | Week Before | SLC | Put together registration packets
3 | March | Week Before | SLC | Review schedules of judges, advisors, state officers, HQ people, etc.
3 | March | Week Before | SLC | Revise script to include retiring advisors, special announcements, etc.
3 | March | Week Before | SLC | Write thank you notes to speakers
3 | March | ZZZ--Evening Before | SLC | Bring back-up cameras for additional photo opportunities
3 | March | ZZZ--Evening Before | SLC | Determine who will register students
3 | March | ZZZ--Evening Before | SLC | Determine who will take photos as chapters arrive
3 | March | ZZZ--Evening Before | SLC | Put together registration packets
3 | March | ZZZ--Evening Before | SLC | Rehearse business meeting with state officers
3 | March | ZZZ--Evening Before | SLC | Rehearse opening session with state officers
3 | March | ZZZ--Evening Before | SLC | Set up Headquarters
4 | April | Early | SLC | Hold State Officer/Executive Committee Meeting for Follow-up
4 | April | Late | NLC | Send off Statements of Assurances to Nationals
5 | May | Early | SLC | Determine possible venues for event
5 | May | Early | FLC | Email all advisors regarding date
5 | May | Early | FLC | Secure location for Advisors' Meeting
5 | May | Early | FLC | Secure Statehouse for next fall’s date
5 | April | Late | NLC | Provide Nationals with listing of VT judges
5 | May | Mid | SLC | Visit potential venues for event
6 | June | Early | NLC | Gather itineraries from local advisors
6 | June | Early | NLC | Plan VT meeting during Nationals
6 | June | Early | FLC | Request breakfast snack options/prices
6 | June | Early | FLC | Secure hotel for night before for state officers
6 | June | Early | SLC | Sign contract for event
7 | July | Mid | SOT | Attend with state officers
7 | July | Mid | SOT | Meet with Executive Committee
7 | July | Mid | SOT | Work on Program of Work
8 | August | Mid | FLC | Contact WCAX and other media to cover event
8 | August | Mid | FLC | Determine agenda for day
8 | August | Mid | FLC | Determine registration deadline
8 | August | Mid | FLC | Determine thank you gifts for speakers
8 | August | Mid | FLC | Get Secretary's Report for program
8 | August | Mid | FLC | Get Treasurer's Report for program
8 | August | Mid | FLC | Get workshop speakers' needs (AV, pens, flipchart, etc.)
8 | August | Mid | FLC | Plan registration process
8 | August | Mid | FLC | Secure keynote speaker
8 | August | Mid | FLC | Secure workshop speaker(s)
8 | August | Mid | FLC | Solicit door prizes
8 | August | Mid | FLC | Update website to include dates and registration process
9 | September | Early | SLC | Determine approximate costs for event
9 | September | Early | FLC | Determine door prize process (tickets, names from registration, etc.)
9 | September | Early | FLC | Determine which state officers will help each workshop presenter
9 | September | Early | FLC | Email registrations/registration process to advisors
9 | September | Early | FLC | Plan Advisors' Meeting agenda
9 | September | Early | SLC | Post conference dates on website
9 | September | Week Before | FLC | Adjust script as necessary
9 | September | Week Before | FLC | Create evaluation form
9 | September | Week Before | FLC | Create nametags for attendees
9 | September | Week Before | FLC | Create program
9 | September | Week Before | FLC | Determine who will register students that morning
9 | September | Week Before | FLC | Determine who will take photos as chapters arrive
9 | September | Week Before | FLC | Print Advisors' Meeting agenda
9 | September | Week Before | FLC | Print Certificates of Participation
9 | September | Week Before | FLC | Print evaluation form
9 | September | Week Before | FLC | Print program
9 | September | Week Before | FLC | Provide cafeteria with lunch numbers
9 | September | Week Before | FLC | Purchase envelopes for registration packets
9 | September | Week Before | FLC | Purchase nametags for registration packets
9 | September | Week Before | FLC | Purchase thank you gifts for speakers
9 | September | Week Before | FLC | Put together registration packets
9 | September | Week Before | FLC | Write thank you notes to speakers
10 | October | Evening Before | FLC | Rehearse business meeting with state officers
10 | October | Evening Before | FLC | Rehearse opening session with state officers
10 | October | Event Day | FLC | Announce Pin and T-shirt Design Contest
10 | October | Event Day | FLC | Bring back-up cameras for additional photo opportunities
10 | October | Mid | SLC | Post pin and t-shirt design contest on website
12 | December | Early | SLC | Determine registration deadline
12 | December | Early | SLC | Determine thank you gifts for speakers & judges
12 | December | Early | SLC | Determine winner of pin design
12 | December | Early | SLC | Determine winner of t-shirt design
12 | December | Early | SLC | Meet with Executive Committee
12 | December | Early | SLC | Plan registration process
12 | December | Early | SLC | Receive pin designs
12 | December | Early | SLC | Receive t-shirt designs
12 | December | Early | SLC | Secure keynote speaker
12 | December | Mid | SLC | Update website to include dates and registration process